# PROJECT CHARTER TEMPLATE

# PROJECT INFORMATION

| PROJECT NAME |  |  | PROJECT MANAGER | PROJECT SPONSOR |
| --- | --- | --- | --- | --- |
| Customer Churn Prediction – StreamFlix |  |  | Béla | Head of Marketing – StreamFlix (Fictional company) |
| EMAIL |  | PHONE | ORGANIZATIONAL UNIT(S) |  |
| streamflix@streamflix.com |  | +36 1 482 5522 | Marketing department, Data analytics team |  |
| GREEN BELTS ASSIGNED |  |  | EXPECTED START DATE | EXPECTED COMPLETION DATE |
| Fabó Leon Tompos, Levente Sélley, Gergő Zalaváry |  |  | 2026.02 | 2026.05 |
| BLACK BELTS ASSIGNED |  |  | EXPECTED SAVINGS | ESTIMATED COSTS |
| Tibor Kovács |  |  | €600.000 annual (estimated 10% churn reduction) | no real infrastructure cost |

PROJECT OVERVIEW

| PROBLEM OR ISSUE | The company experiences monthly customer churn. Losing subscribers reduces recurring revenue and increases customer acquisition costs. |
| --- | --- |
| PURPOSE OF PROJECT | To develop a machine learning model that predicts which customers are likely to churn, enabling targeted retention strategies. |
| BUSINESS CASE | Reducing churn by even a small percentage significantly increases profitability in subscription-based businesses. Predictive analytics allows proactive customer retention instead of reactive measures. |
| GOALS / METRICS | - Build classification model to predict churn (Churned: 1/0) - Achieve minimum 75% accuracy - Identify top churn-driving features - Provide actionable business recommendations |
| EXPECTED DELIVERABLES | - Cleaned and prepared dataset - Exploratory data analysis report - Trained and evaluated ML models - Model comparison results - Business recommendation report - Final presentation |

PROJECT SCOPE

| WITHIN SCOPE | - Data cleaning and preprocessing - Exploratory data analysis - Feature engineering - Model training (Logistic regression, Random forest, XGBoost) - Model evaluation - Business interpretation - High-level deployment proposal |
| --- | --- |
| OUTSIDE OF SCOPE | - Real production deployment - Real-time system integration - Live customer intervention - Legal/privacy compliance implementation |

TENTATIVE SCHEDULE

| KEY MILESTONE | START | FINISH |
| --- | --- | --- |
| Project definition | 16 February | 1 March |
| Data understanding, cleaning | 23 February | 15 March |
| Exploratory data analysis | 15 March | 29 March |
| Model development | 29 March | 19 April |
| Model evaluation, optimization | 19 April | 3 May |
| Business recommendations | 3 May | 10 May |
| Final presentation | 10 May | 17 May |

RESOURCES

| PROJECT TEAM | Fabó Leon Tompos, Levente Sélley, Gergő Zalaváry |  |
| --- | --- | --- |
| SUPPORT RESOURCES | Kaggle dataset documentation Python (Pandas, Scikit-learn, XGBoost) |  |
| SPECIAL NEEDS | Laptop with Python environment Jupyter Notebook PowerPoint for presentation |  |

COSTS

| COST TYPE | VENDOR / LABOR NAMES |  | RATE | QTY | AMOUNT |
| --- | --- | --- | --- | --- | --- |
| Labour | employees work |  | €20/h | 3 people * 20 h/ week * 24 weeks | €28.800 |
| Development cost | Open-source tools pPid packages |  | ~€1.000 one time | - | €1.000 |
| Hardware | Existing work laptops amortization |  | €2/week | 3 people * €2/week * 24 weeks | €144 |
| Software | Python (open source) Optional deployment in cloud (serverbased) |  | €50/month | 2 instances (prod, test)* 3 month | €300 |
|  |  |  | TOTAL COSTS |  | €30.244 |

BENEFITS AND CUSTOMERS

| PROCESS OWNER | Marketing analytics manager |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| KEY STAKEHOLDERS | Marketing team Customer retention team Management |  |  |  |  |
| FINAL CUSTOMER | StreamFlix subscribers |  |  |  |  |
| EXPECTED BENEFITS | - Reduced churn rate - Increased customer lifetime value - Better targeting of retention campaigns - Data-driven decision making |  |  |  |  |
| TYPE OF BENEFIT | BASIS OF ESTIMATE |  |  |  | ESTIMATED BENEFIT AMOUNT |
| Revenue retention | 100.000 subsribers, €5/month, €6M annual income, 20% yearly churn rate €1.2M annual loss. from 20% to 10% churn rate means €600K saved anually |  |  |  | €600.000 annually |
|  |  |  | TOTAL BENEFIT |  |  |

RISKS, CONSTRAINTS, AND ASSUMPTIONS

| RISKS | - Imbalanced dataset - Overfitting models - Missing or noisy data - Model performance below expectations |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| CONSTRAINTS | - Limited computational resources - Limited to existing customer data - Must fit current IT systems and budget - Must comply with data protection regulations |  |  |  |  |  |
| ASSUMPTIONS | - Past behaviour predicts future churn - Marketing will use the predictions - Targeted actions can reduce churn |  |  |  |  |  |
| PREPARED BY |  | TITLE |  |  |  | DATE |
| Fabó Leon Tompos, Levente Sélley, Gergő Zalaváry |  | Data Science project |  |  |  | 2026.02.24 |

https://www.kaggle.com/datasets/akashanandt/streaming-service-data